## REQM
CMMI-2 - Requirements Management | # NA | # ? | Score | P1
SP 1.1 Obtain an Understanding of Requirements |  |  | 7 | 7
SP 1.2 Obtain Commitment to Requirements |  |  | 8 | 8
SP 1.3 Manage Requirements Changes |  |  | 4 | 4
SP 1.4 Maintain Bi-directional Traceability of Requirements |  |  | 4 | 4
SP 1.5 Identify inconsistencies between project work & req. |  |  | 8 | 8
GP 2.1 Establish an Organizational Policy |  |  | 4 | 4
GP 2.2 Plan the Process |  |  | 6 | 6
GP 2.3 Provide Resources |  |  | 4 | 4
GP 2.4 Assign Responsibility |  |  | 8 | 8
GP 2.5 Train People |  |  | 7 | 7
GP 2.6 Manage Configurations |  |  | 8 | 8
GP 2.7 Identify and Involve Relevant Stakeholders |  |  | 5 | 5
GP 2.8 Monitor and Control the Process |  |  | 9 | 9
GP 2.9 Objectively Evaluate Adherence |  |  | 7 | 7
GP 2.10 Review Status with Higher Level Management |  |  | 5 | 5
GP 3.1 Establish a Defined Process (*) |  |  | 4 | 4
GP 3.2 Collect Improvement Information (*) |  |  | 4 | 4
| Total score |  | 6
(*) not expected for a maturity level 2 rating

## PP
CMMI-2 - Project Planning | # NA | # ? | Score | P1
SP 1.1 Estimate the Scope of the Project |  |  | 10 | 10
SP 1.2 Establish Estimates of Work Product and Task Attributes |  |  | 10 | 10
SP 1.3 Define Project Life Cycle |  |  | 5 | 5
SP 1.4 Determine Estimates of Effort and Cost |  |  | 10 | 10
SP 2.1 Establish the Budget and Schedule |  |  | 10 | 10
SP 2.2 Identify Project Risks |  |  | 10 | 10
SP 2.3 Plan for Data Management |  |  | 2 | 2
SP 2.4 Plan for Project Resources |  |  | 2 | 2
SP 2.5 Plan for Needed Knowledge and Skills |  |  | 5 | 5
SP 2.6 Plan Stakeholder Involvement |  |  | 10 | 10
SP 2.7 Establish the Project Plan |  |  | 10 | 10
SP 3.1 Review Plans that Affect the Project |  |  | 5 | 5
SP 3.2 Reconcile Work and Resource Levels |  |  | 0 | 0
SP 3.3 Obtain Plan Commitment |  |  | 10 | 10
GP 2.1 Establish an Organizational Policy |  |  | 10 | 10
GP 2.2 Plan the Process |  |  | 0 | 0
GP 2.3 Provide Resources |  |  | 10 | 10
GP 2.4 Assign Responsibility |  |  | 10 | 10
GP 2.5 Train People |  |  | 10 | 10
GP 2.6 Manage Configurations |  |  | 10 | 10
GP 2.7 Identify and Involve Relevant Stakeholders |  |  | 10 | 10
GP 2.8 Monitor and Control the Process |  |  | 0 | 0
GP 2.9 Objectively Evaluate Adherence |  |  | 0 | 0
GP 2.10 Review Status with Higher Level Management |  |  | 0 | 0
GP 3.1 Establish a Defined Process (*) |  |  | 0 | 0
GP 3.2 Collect Improvement Information (*) |  |  | 8 | 8
| Total score |  | 6.4231
(*) not expected for a maturity level 2 rating

## PMC
CMMI-2 - Project Monitoring and Control | # NA | # ? | Score | P1
SP 1.1 Monitor Project Planning Parameters |  |  | 10 | 10
SP 1.2 Monitor Commitments |  |  | 4 | 4
SP 1.3 Monitor Project Risks |  |  | 10 | 10
SP 1.4 Monitor Data Management |  |  | 1 | 1
SP 1.5 Monitor Stakeholder Involvement |  |  | 1 | 1
SP 1.6 Conduct Progress Reviews |  |  | 10 | 10
SP 1.7 Conduct Milestone Reviews |  |  | 1 | 1
SP 2.1 Analyze Issues |  |  | 10 | 10
SP 2.2 Take Correction Action |  |  | 1 | 1
SP 2.3 Manage Corrective Action |  |  | 1 | 1
GP 2.1 Establish an Organizational Policy |  |  | 1 | 1
GP 2.2 Plan the Process |  |  | 1 | 1
GP 2.3 Provide Resources |  |  | 4 | 4
GP 2.4 Assign Responsibility |  |  | 10 | 10
GP 2.5 Train People |  |  | 1 | 1
GP 2.6 Manage Configurations |  |  | 4 | 4
GP 2.7 Identify and Involve Relevant Stakeholders |  |  | 1 | 1
GP 2.8 Monitor and Control the Process |  |  | 1 | 1
GP 2.9 Objectively Evaluate Adherence |  |  | 1 | 1
GP 2.10 Review Status with Higher Level Management |  |  | 1 | 1
GP 3.1 Establish a Defined Process (*) |  |  | 1 | 1
GP 3.2 Collect Improvement Information (*) |  |  | 1 | 1
| Total score |  | 3.4545
(*) not expected for a maturity level 2 rating

## SAM
CMMI-2 - Supplier Agreement Management | # NA | # ? | Score | P1
SP 1.1 Determine Acquisition Type
SP 1.2 Select Suppliers
SP 1.3 Establish Supplier Agreements
SP 2.1 Execute the Supplier Agreement
SP 2.2 Monitor Selected Supplier Processes
SP 2.3 Evaluate Selected Supplier Work Products
SP 2.4 Accept the Acquired Product
SP 2.5 Transition Products
GP 2.1 Establish an Organizational Policy
GP 2.2 Plan the Process
GP 2.3 Provide Resources
GP 2.4 Assign Responsibility
GP 2.5 Train People
GP 2.6 Manage Configurations
GP 2.7 Identify and Involve Relevant Stakeholders
GP 2.8 Monitor and Control the Process
GP 2.9 Objectively Evaluate Adherence
GP 2.10 Review Status with Higher Level Management
GP 3.1 Establish a Defined Process (*)
GP 3.2 Collect Improvement Information (*)
| Total score |  | 0
(*) not expected for a maturity level 2 rating

## MA
CMMI-2 - Measurement and Analysis | # NA | # ? | Score | P1
SP 1.1 Establish Measurement Objectives |  |  | 4 | 4
SP 1.2 Specify Measures |  |  | 5 | 5
SP 1.3 Specify Data Collection and Storage Procedures |  |  | 4 | 4
SP 1.4 Specify Analysis Procedures |  |  | 4 | 4
SP 2.1 Collect Measurement Data |  |  | 5 | 5
SP 2.2 Analyze Measurement Data |  |  | 3 | 3
SP 2.3 Store Data and Results |  |  | 4 | 4
SP 2.3 Communicate Results |  |  | 7 | 7
GP 2.1 Establish an Organizational Policy |  |  | 4 | 4
GP 2.2 Plan the Process |  |  | 4 | 4
GP 2.3 Provide Resources |  |  | 6 | 6
GP 2.4 Assign Responsibility |  |  | 8 | 8
GP 2.5 Train People |  |  | 4 | 4
GP 2.6 Manage Configurations |  |  | 10 | 10
GP 2.7 Identify and Involve Relevant Stakeholders |  |  | 6 | 6
GP 2.8 Monitor and Control the Process |  |  | 6 | 6
GP 2.9 Objectively Evaluate Adherence |  |  | 4 | 4
GP 2.10 Review Status with Higher Level Management |  |  | 6 | 6
GP 3.1 Establish a Defined Process (*) |  |  | 4 | 4
GP 3.2 Collect Improvement Information (*) |  |  | 4 | 4
| Total score |  | 5.1
(*) not expected for a maturity level 2 rating

## PPQA
CMMI-2 - Process and Product Quality Assurance | # NA | # ? | Score | P1
SP 1.1 Objectively Evaluate Processes |  |  | 6 | 6
SP 1.2 Objectively Evaluate Work Products and Services |  |  | 7 | 7
SP 2.1 Communicate & Ensure Resolution of Noncompliances |  |  | 6 | 6
SP 2.2 Establish Records |  |  | 6 | 6
GP 2.1 Establish an Organizational Policy | 1 |  |  | NA
GP 2.2 Plan the Process |  |  | 5 | 5
GP 2.3 Provide Resources |  |  | 4 | 4
GP 2.4 Assign Responsibility |  |  | 5 | 5
GP 2.5 Train People |  |  | 3 | 3
GP 2.6 Manage Configurations |  |  | 5 | 5
GP 2.7 Identify and Involve Relevant Stakeholders | 1 |  |  | NA
GP 2.8 Monitor and Control the Process |  |  | 5 | 5
GP 2.9 Objectively Evaluate Adherence |  |  | 6 | 6
GP 2.10 Review Status with Higher Level Management | 1 |  |  | NA
GP 3.1 Establish a Defined Process (*)
GP 3.2 Collect Improvement Information (*)
| Total score |  | 4.1429
(*) not expected for a maturity level 2 rating

## CM
CMMI-2 - Configuration Management | # NA | # ? | Score | P1
SP 1.1 Identify Configuration Items |  |  | 7 | 7
SP 1.2 Establish a Configuration Management System |  |  | 7 | 7
SP 1.3 Create or Release Baselines |  |  | 5 | 5
SP 2.1 Track Change Requests |  |  | 4 | 4
SP 2.2 Control Configuration Items |  |  | 7 | 7
SP 3.1 Establish Configuration Management Records |  |  | 5 | 5
SP 3.2 Perform Configuration Audits |  |  | 6 | 6
GP 2.1 Establish an Organizational Policy |  |  | 4 | 4
GP 2.2 Plan the Process |  |  | 6 | 6
GP 2.3 Provide Resources |  |  | 6 | 6
GP 2.4 Assign Responsibility |  |  | 7 | 7
GP 2.5 Train People |  |  | 4 | 4
GP 2.6 Manage Configurations |  |  | 8 | 8
GP 2.7 Identify and Involve Relevant Stakeholders |  |  | 8 | 8
GP 2.8 Monitor and Control the Process |  |  | 6 | 6
GP 2.9 Objectively Evaluate Adherence |  |  | 5 | 5
GP 2.10 Review Status with Higher Level Management |  |  | 4 | 4
GP 3.1 Establish a Defined Process (*) |  |  | 4 | 4
GP 3.2 Collect Improvement Information (*) |  |  | 4 | 4
| Total score |  | 5.6316
(*) not expected for a maturity level 2 rating

## RD
CMMI-2 - Requirements Development | # NA | # ? | Score | P1
SP 1.1 Elicit Needs
SP 1.2 Develop Customer Requirements
SP 2.1 Establish Product and Product Component Req.
SP 2.2 Allocate Product Component Requirements
SP 2.3 Identify Interface Requirements
SP 3.1 Establish Operational Concepts and Scenarios
SP 3.2 Establish a Definition of Required Functionality
SP 3.3 Analyze Requirements
SP 3.4 Analyze Requirements to Achieve Balance
SP 3.5 Validate Requirements
GP 2.1 Establish an Organizational Policy
GP 2.2 Plan the Process
GP 2.3 Provide Resources
GP 2.4 Assign Responsibility
GP 2.5 Train People
GP 2.6 Manage Configurations
GP 2.7 Identify and Involve Relevant Stakeholders
GP 2.8 Monitor and Control the Process
GP 2.9 Objectively Evaluate Adherence
GP 2.10 Review Status with Higher Level Management
GP 3.1 Establish a Defined Process
GP 3.2 Collect Improvement Information
| Total score |  | 0

## TS
CMMI-2 - Technical Solution | # NA | # ? | Score | P1
SP 1.1 Develop Alternative Solutions and Selection Criteria
SP 1.2 Select Product Component Solutions
SP 2.1 Design the Product or Product Component
SP 2.2 Establish a Technical Data Package
SP 2.3 Design Interfaces using Criteria
SP 2.4 Perform Make, Buy, or Reuse Analyses
SP 3.1 Implement the Design
SP 3.2 Develop Product Support Documentation
GP 2.1 Establish an Organizational Policy
GP 2.2 Plan the Process
GP 2.3 Provide Resources
GP 2.4 Assign Responsibility
GP 2.5 Train People
GP 2.6 Manage Configurations
GP 2.7 Identify and Involve Relevant Stakeholders
GP 2.8 Monitor and Control the Process
GP 2.9 Objectively Evaluate Adherence
GP 2.10 Review Status with Higher Level Management
GP 3.1 Establish a Defined Process
GP 3.2 Collect Improvement Information
| Total score |  | 0

## PI
CMMI-2 - Product Integration | # NA | # ? | Score | P1
SP 1.1 Determine Product Integration Sequence
SP 1.2 Establish the Product Integration Environment
SP 1.3 Establish Product Integration Procedures and Criteria
SP 2.1 Review Interface Descriptions for Completeness
SP 2.2 Manage Interfaces
SP 3.1 Confirm Readiness of Product Comp. for Integration
SP 3.2 Assemble Product Components
SP 3.3 Evaluate Assembled Product Components
SP 3.4 Package and Deliver the Product or Product Component
GP 2.1 Establish an Organizational Policy
GP 2.2 Plan the Process
GP 2.3 Provide Resources
GP 2.4 Assign Responsibility
GP 2.5 Train People
GP 2.6 Manage Configurations
GP 2.7 Identify and Involve Relevant Stakeholders
GP 2.8 Monitor and Control the Process
GP 2.9 Objectively Evaluate Adherence
GP 2.10 Review Status with Higher Level Management
GP 3.1 Establish a Defined Process
GP 3.2 Collect Improvement Information
| Total score |  | 0

## VER
CMMI-2 - Verification | # NA | # ? | Score | P1
SP 1.1 Select Work Product for Verification
SP 1.2 Establish the Verification Environment
SP 1.3 Establish Verification Procedures and Criteria
SP 2.1 Prepare for Peer Reviews
SP 2.2 Conduct Peer Reviews
SP 2.3 Analyze Peer Review Data
SP 3.1 Perform Verification
SP 3.2 Analyze Verification Results
GP 2.1 Establish an Organizational Policy
GP 2.2 Plan the Process
GP 2.3 Provide Resources
GP 2.4 Assign Responsibility
GP 2.5 Train People
GP 2.6 Manage Configurations
GP 2.7 Identify and Involve Relevant Stakeholders
GP 2.8 Monitor and Control the Process
GP 2.9 Objectively Evaluate Adherence
GP 2.10 Review Status with Higher Level Management
GP 3.1 Establish a Defined Process
GP 3.2 Collect Improvement Information
| Total score |  | 0

## VAL
CMMI-2 - Validation | # NA | # ? | Score | P1
SP 1.1 Select Work Products for Validation
SP 1.2 Establish the Validation Environment
SP 1.3 Establish Validation Procedures and Criteria
SP 2.1 Perform Validation
SP 2.2 Analyze Validation Results
GP 2.1 Establish an Organizational Policy
GP 2.2 Plan the Process
GP 2.3 Provide Resources
GP 2.4 Assign Responsibility
GP 2.5 Train People
GP 2.6 Manage Configurations
GP 2.7 Identify and Involve Relevant Stakeholders
GP 2.8 Monitor and Control the Process
GP 2.9 Objectively Evaluate Adherence
GP 2.10 Review Status with Higher Level Management
GP 3.1 Establish a Defined Process
GP 3.2 Collect Improvement Information
| Total score |  | 0

## OPF
CMMI-3 - Organizational Process Focus | # NA | # ? | Score | P1
SP 1.1 Establish Organizational Process Needs
SP 1.2 Appraise the Organization’s Processes
SP 1.3 Identify the Organization's Process Improvements
SP 2.1 Establish Process Action Plans
SP 2.2 Implement Process Action Plans
SP 3.1 Deploy Organizational Process Assets
SP 3.2 Deploy Standard Processes
SP 3.3 Monitor Implementation
SP 3.4 Incorporate Proc.-Related Exp. into the Org. Proc. Assets
GP 2.1 Establish an Organizational Policy
GP 2.2 Plan the Process
GP 2.3 Provide Resources
GP 2.4 Assign Responsibility
GP 2.5 Train People
GP 2.6 Manage Configurations
GP 2.7 Identify and Involve Relevant Stakeholders
GP 2.8 Monitor and Control the Process
GP 2.9 Objectively Evaluate Adherence
GP 2.10 Review Status with Higher Level Management
GP 3.1 Establish a Defined Process
GP 3.2 Collect Improvement Information
| Total score |  | 0

## OPD
CMMI-3 - Organizational Process Definition | # NA | # ? | Score | P1
SP 1.1 Establish Standard Processes
SP 1.2 Establish Life-Cycle Model Descriptions
SP 1.3 Establish Tailoring Criteria and Guidelines
SP 1.4 Establish the Organization’s Measurement Repository
SP 1.5 Establish the Organization’s Process Asset Library
SP 1.6 Establish Work Environment Standards
SP 2.1 (IPPD only) Establish Empowerment Mechanisms
SP 2.2 (IPPD only) Establish Rules/Guidelines for Integr. Teams
SP 2.3 (IPPD only) Balance Team & Home Organization Resp.
GP 2.1 Establish an Organizational Policy
GP 2.2 Plan the Process
GP 2.3 Provide Resources
GP 2.4 Assign Responsibility
GP 2.5 Train People
GP 2.6 Manage Configurations
GP 2.7 Identify and Involve Relevant Stakeholders
GP 2.8 Monitor and Control the Process
GP 2.9 Objectively Evaluate Adherence
GP 2.10 Review Status with Higher Level Management
GP 3.1 Establish a Defined Process
GP 3.2 Collect Improvement Information
| Total score |  | 0

## OT
CMMI-3 - Organizational Training | # NA | # ? | Score | P1
SP 1.1 Establish the Strategic Training needs
SP 1.2 Determine Which Training Needs Are Resp. of Organiz.
SP 1.3 Establish Organizational Training Tactical Plan
SP 1.4 Establish Training Capability
SP 2.1 Deliver Training
SP 2.2 Establish Training Records
SP 2.3 Assess Training Effectiveness
GP 2.1 Establish an Organizational Policy
GP 2.2 Plan the Process
GP 2.3 Provide Resources
GP 2.4 Assign Responsibility
GP 2.5 Train People
GP 2.6 Manage Configurations
GP 2.7 Identify and Involve Relevant Stakeholders
GP 2.8 Monitor and Control the Process
GP 2.9 Objectively Evaluate Adherence
GP 2.10 Review Status with Higher Level Management
GP 3.1 Establish a Defined Process
GP 3.2 Collect Improvement Information
| Total score |  | 0

## IPM
CMMI-3 - Integrated Project Management | # NA | # ? | Score | P1
SP 1.1 Establish the Project’s Defined Process
SP 1.2 Use Org. Process Assets for Planning Project Activities
SP 1,3 Establish the Project's Work Environment
SP 1.4 Integrate Plans
SP 1.5 Manage the Project Using the Integrated Plans
SP 1.6 Contribute to the Organization’s Process Assets
SP 2.1 Manage Stakeholder Involvement
SP 2.2 Manage Dependencies
SP 2.3 Resolve Coordination Issues
SP 3.1 (IPPD only) Establish the Project’s Shared Vision
SP 3.2 (IPPD only) Establish the Integrated Team Structure
SP 3.3 (IPPD only) Allocate Requirements to Integrated Teams
SP 3.4 (IPPD only) Establish Integrated Teams
SP 3.5 (IPPD only) Ensure Collaboration among Interfacing Teams
GP 2.1 Establish an Organizational Policy
GP 2.2 Plan the Process
GP 2.3 Provide Resources
GP 2.4 Assign Responsibility
GP 2.5 Train People
GP 2.6 Manage Configurations
GP 2.7 Identify and Involve Relevant Stakeholders
GP 2.8 Monitor and Control the Process
GP 2.9 Objectively Evaluate Adherence
GP 2.10 Review Status with Higher Level Management
GP 3.1 Establish a Defined Process
GP 3.2 Collect Improvement Information
| Total score |  | 0

## RSKM
CMMI-3 - Risk Management | # NA | # ? | Score | P1
SP 1.1 Determine Risk Sources and Categories
SP 1.2 Define Risk Parameters
SP 1.3 Establish a Risk Management Strategy
SP 2.1 Identify Risks
SP 2.2 Evaluate, Categorize, and Prioritize Risks
SP 3.1 Develop Risk Mitigation Plans
SP 3.2 Implement Risk Mitigation Plans
GP 2.1 Establish an Organizational Policy
GP 2.2 Plan the Process
GP 2.3 Provide Resources
GP 2.4 Assign Responsibility
GP 2.5 Train People
GP 2.6 Manage Configurations
GP 2.7 Identify and Involve Relevant Stakeholders
GP 2.8 Monitor and Control the Process
GP 2.9 Objectively Evaluate Adherence
GP 2.10 Review Status with Higher Level Management
GP 3.1 Establish a Defined Process
GP 3.2 Collect Improvement Information
| Total score |  | 0

## DAR
CMMI-3 - Decision Analysis and Resolution | # NA | # ? | Score | P1
SP 1.1 Establish Guidelines for Decision Analysis
SP 1.2 Establish Evaluation Criteria
SP 1.3 Identify Alternative Solutions
SP 1.4 Select Evaluation Methods
SP 1.5 Evaluate Alternatives
SP 1.6 Select Solutions
GP 2.1 Establish an Organizational Policy
GP 2.2 Plan the Process
GP 2.3 Provide Resources
GP 2.4 Assign Responsibility
GP 2.5 Train People
GP 2.6 Manage Configurations
GP 2.7 Identify and Involve Relevant Stakeholders
GP 2.8 Monitor and Control the Process
GP 2.9 Objectively Evaluate Adherence
GP 2.10 Review Status with Higher Level Management
GP 3.1 Establish a Defined Process
GP 3.2 Collect Improvement Information
| Total score |  | 0

## OPP
CMMI-4 - Organizational Process Performance | # NA | # ? | Score | P1
SP 1.1 Select Processes
SP 1.2 Establish Process Performance Measures
SP 1.3 Establish Quality and Process Performance Objectives
SP 1.4 Establish Process Performance Baselines
SP 1.5 Establish Process Performance Models
GP 2.1 Establish an Organizational Policy
GP 2.2 Plan the Process
GP 2.3 Provide Resources
GP 2.4 Assign Responsibility
GP 2.5 Train People
GP 2.6 Manage Configurations
GP 2.7 Identify and Involve Relevant Stakeholders
GP 2.8 Monitor and Control the Process
GP 2.9 Objectively Evaluate Adherence
GP 2.10 Review Status with Higher Level Management
GP 3.1 Establish a Defined Process
GP 3.2 Collect Improvement Information
| Total score |  | 0

## QPM
CMMI-4 - Quantitative Project Management | # NA | # ? | Score | P1
SP 1.1 Establish the Project’s Objectives
SP 1.2 Compose the Defined Process
SP 1.3 Select the Sub-processes to be Statiscally Managed
SP 1.4 Manage Project Performance
SP 2.1 Select Measures and Analytic Techniques
SP 2.2 Apply Statistical Methods to Understand Variation
SP 2.3 Monitor Performance of the Selected Sub-processes
SP 2.4 Record Statistical Management Data
GP 2.1 Establish an Organizational Policy
GP 2.2 Plan the Process
GP 2.3 Provide Resources
GP 2.4 Assign Responsibility
GP 2.5 Train People
GP 2.6 Manage Configurations
GP 2.7 Identify and Involve Relevant Stakeholders
GP 2.8 Monitor and Control the Process
GP 2.9 Objectively Evaluate Adherence
GP 2.10 Review Status with Higher Level Management
GP 3.1 Establish a Defined Process
GP 3.2 Collect Improvement Information
| Total score |  | 0

## OID
CMMI-5 - Organizational Innovation and Deployment | # NA | # ? | Score | P1
SP 1.1 Collect and Analyze Improvement Proposals
SP 1.2 Identify and Analyze Innovations
SP 1.3 Pilot Improvements
SP 1.4 Select Improvements for Deployment
SP 2.1 Plan the Deployment
SP 2.2 Manage the Deployment
SP 2.3 Measure Improvement Effects
GP 2.1 Establish an Organizational Policy
GP 2.2 Plan the Process
GP 2.3 Provide Resources
GP 2.4 Assign Responsibility
GP 2.5 Train People
GP 2.6 Manage Configurations
GP 2.7 Identify and Involve Relevant Stakeholders
GP 2.8 Monitor and Control the Process
GP 2.9 Objectively Evaluate Adherence
GP 2.10 Review Status with Higher Level Management
GP 3.1 Establish a Defined Process
GP 3.2 Collect Improvement Information
| Total score |  | 0

## CAR
CMMI-5 - Causal Analysis and Resolution | # NA | # ? | Score | P1
SP 1.1 Select Defect Data for Analysis
SP 1.2 Analyze Causes
SP 2.1 Implement the Action Proposals
SP 2.2 Evaluate the Effect of Changes
SP 2.3 Record Data
GP 2.1 Establish an Organizational Policy
GP 2.2 Plan the Process
GP 2.3 Provide Resources
GP 2.4 Assign Responsibility
GP 2.5 Train People
GP 2.6 Manage Configurations
GP 2.7 Identify and Involve Relevant Stakeholders
GP 2.8 Monitor and Control the Process
GP 2.9 Objectively Evaluate Adherence
GP 2.10 Review Status with Higher Level Management
GP 3.1 Establish a Defined Process
GP 3.2 Collect Improvement Information
| Total score |  | 0

## Report (hidden)
Interim Maturity Evaluation Report
Date (Year)
Date (Month-Day)
Number of participants
CMMI Level 2
Requirements Management
Project Planning
Project Monitoring and Control
Supplier Agreement Management
Measurement and Analysis
Process/Product Quality Assurance
Configuration Management
CMMI Level 3
Requirements Development
Technical Solution
Product Integration
Verification
Validation
Organizational Process Focus
Organizational Process Definition
Organizational Training
Integrated Project Management
Risk Management
Decision Analysis and Resolution
CMMI Level 4 and 5
Organizational Process Performance
Quantitative Project Management
Organizational Innovation and Deployment
Causal Analysis and Resolution
Level 2
|  | Requirements Management | NA | ? | Score
| SP 1.1 | Obtain an Understanding of Requirements Develop an understanding with the requirements providers on the meaning of the requirements |  |  | 7
| SP 1.2 | Obtain Commitment to Requirements Obtain commitment to the requirements from the project participants |  |  | 8
| SP 1.3 | Manage Requirements Changes Manage changes to the requirements as they evolve during the project |  |  | 4
| SP 1.4 | Maintain Bi-directional Traceability of Requirements Maintain bi-directional traceability among the requirements and work products |  |  | 4
| SP 1.5 | Identify Inconsistencies between Project Work and Requirements Identify inconsistencies between the project plans and work products and the requirements |  |  | 8
| GP 2.1 | (Establish an Organizational Policy Establish and maintain an organizational policy for planning and performing the requirements management process |  |  | 4
| GP 2.2 | Plan the Process Establish and maintain the plan for performing the requirements management process |  |  | 6
| GP 2.3 | Provide Resources Provide adequate resources for performing the requirements management process, developing the work products and providing the services of the process |  |  | 4
| GP 2.4 | Assign Responsibility Assign responsibility and authority for performing the process, developing the work products, and providing the services of the requirements management process |  |  | 8
| GP 2.5 | Train People Train the people performing or supporting the requirements management process as needed |  |  | 7
| GP 2.6 | Manage Configurations Place designated work products of the requirements management process under appropriate levels of control |  |  | 8
| GP 2.7 | Identify and Involve Relevant Stakeholders Identify and involve the relevant stakeholders of the requirements management process as planned |  |  | 5
| GP 2.8 | Monitor and Control the Process Monitor and control the requirements management process against the plan for performing the process and take appropriate corrective action |  |  | 9
| GP 2.9 | Objectively Evaluate Adherence Objectively evaluate adherence of the requirements management process against its process description, standards, and procedures, and address noncompliance |  |  | 7
| GP 2.10 | Review Status with Higher-Level Management Review the activities, status, and results of the requirements management process with higher level management and resolve issues |  |  | 5
| GP 3.1 | Establish a Defined Process Establish and maintain the description of a defined requirements management process |  |  | 4
| GP 3.2 | Collect Improvement Information Collect work products, measures, measurement results, and improvement information derived from planning and performing the requirements management process to support the future use and improvement of the organization's processes and process assets |  |  | 4
|  | Project Planning |  |  | Score
| SP 1.1 | Estimate the Scope of the Project Establish a top-level work breakdown structure (WBS) to estimate of the scope of the project |  |  | 10
| SP 1.2 | Establish Estimates of Work Product and Task Attributes Establish and maintain estimates of the attributes of the work products and tasks |  |  | 10
| SP 1.3 | Define Project Life Cycle Define the project life-cycle phases on which to scope the planning effort |  |  | 5
| SP 1.4 | Determine Estimates of Effort and Cost Estimate the project effort and cost for the work products and tasks based on estimation rationale |  |  | 10
| SP 2.1 | Establish the Budget and Schedule Establish and maintain the project's budget and schedule |  |  | 10
| SP 2.2 | Identify Project Risks Identify and analyze project risks |  |  | 10
| SP 2.3 | Plan for Data Management Plan for the management of project data |  |  | 2
| SP 2.4 | Plan for Project Resources Plan for necessary resources to perform the project |  |  | 2
| SP 2.5 | Plan for Needed Knowledge and Skills Plan for knowledge and skills needed to perform the project |  |  | 5
| SP 2.6 | Plan Stakeholder Involvement Plan the involvement with identified stakeholders |  |  | 10
| SP 2.7 | Establish the Project Plan Establish and maintain the overall project plan content |  |  | 10
| SP 3.1 | Review Plans that Affect the Project Review all plans that affect the project to understand project commitments |  |  | 5
| SP 3.2 | Reconcile Work and Resource Levels Reconcile the project plan to reflect available and estimated resources |  |  | 0
| SP 3.3 | Obtain Plan Commitment Obtain commitment from relevant stakeholders responsible for performing and supporting plan execution |  |  | 10
| GP 2.1 | Establish an Organizational Policy Establish and maintain an organizational policy for planning and performing the project planning process |  |  | 10
| GP 2.2 | Plan the Process Establish and maintain the plan for performing the project planning process |  |  | 0
| GP 2.3 | Provide Resources Provide adequate resources for performing the project planning process, developing the work products and providing the services of the process |  |  | 10
| GP 2.4 | Assign Responsibility Assign responsibility and authority for performing the process, developing the work products, and providing the services of the project planning process |  |  | 10
| GP 2.5 | Train People Train the people performing or supporting the project planning process as needed |  |  | 10
| GP 2.6 | Manage Configurations Place designated work products of the project planning process under appropriate levels of configuration management |  |  | 10
| GP 2.7 | Identify and Involve Relevant Stakeholders Identify and involve the relevant stakeholders of the project planning process as planned |  |  | 10
| GP 2.8 | Monitor and Control the Process Monitor and control the project planning process against the plan for performing the process and take appropriate corrective action |  |  | 0
| GP 2.9 | Objectively Evaluate Adherence Objectively evaluate adherence of the project planning process against its process description, standards, and address noncompliance |  |  | 0
| GP 2.10 | Review Status with Higher-Level Management Review the activities, status, and results of the project planning process with higher level management and resolve issues |  |  | 0
| GP 3.1 | Establish a Defined Process Establish and maintain the description of a defined project planning process |  |  | 0
| GP 3.2 | Collect Improvement Information Collect work products, measures, measurement results, and improvement information derived from planning and performing the project planning process to support the future use and improvement of the organization's processes and process assets |  |  | 8
|  | Project Monitoring and Control |  |  | Score
| SP 1.1 | Monitor Project Planning Parameters Monitor the actual values of the project planning parameters against the project plan |  |  | 10
| SP 1.2 | Monitor Commitments Monitor commitments against those identified in the project plan |  |  | 4
| SP 1.3 | Monitor Project Risks Monitor risks against those identified in the project plan |  |  | 10
| SP 1.4 | Monitor Data Management Monitor the management of project data against the project plan |  |  | 1
| SP 1.5 | Monitor Stakeholder Involvement Monitor stakeholder involvement against the project plan |  |  | 1
| SP 1.6 | Conduct Progress Reviews Periodically review the project's progress, performance, and issues |  |  | 10
| SP 1.7 | Conduct Milestone Reviews Review the accomplishments and results of the project at selected project milestones |  |  | 1
| SP 2.1 | Analyze Issues Collect and analyze the issues and determine the corrective actions necessary to address the issues |  |  | 10
| SP 2.2 | Take Correction Action Take corrective action on identified issues |  |  | 1
| SP 2.3 | Manage Corrective Action Manage corrective actions to closure |  |  | 1
| GP 2.1 | Establish an Organizational Policy Establish and maintain an organizational policy for planning and performing the project monitoring and control process |  |  | 1
| GP 2.2 | Plan the Process Establish and maintain the plan for performing the project monitoring and control process |  |  | 1
| GP 2.3 | Provide Resources Provide adequate resources for performing the project monitoring and control process, developing the work products, and providing the services of the process |  |  | 4
| GP 2.4 | Assign Responsibility Assign responsibility and authority for performing the process, developing the work products, and providing the services of the project monitoring and control process |  |  | 10
| GP 2.5 | Train People Train the people performing or supporting the project monitoring and control process as needed |  |  | 1
| GP 2.6 | Manage Configurations Place designated work products of the project monitoring and control process under appropriate levels of configuration management |  |  | 4
| GP 2.7 | Identify and Involve Relevant Stakeholders Identify and involve the relevant stakeholders of the project monitoring and control process as planned |  |  | 1
| GP 2.8 | Monitor and Control the Process Monitor and control the project monitoring and control process against the plan for performing the process and take appropriate corrective action |  |  | 1
| GP 2.9 | Objectively Evaluate Adherence Objectively evaluate adherence of the project monitoring and control process against its process description, standards, and procedures, and address noncompliance |  |  | 1
| GP 2.10 | Review Status with Higher-Level Management Review the activities, status, and results of the project monitoring and control process with management and resolve issues |  |  | 1
| GP 3.1 | Establish a Defined Process Establish and maintain the description of a defined project monitoring and control process |  |  | 1
| GP 3.2 | Collect Improvement Information Collect work products, measures, measurement results, and improvement information derived from planning and performing the project monitoring and control process to support the future use and improvement of the organization’s processes and process assets |  |  | 1
|  | Supplier Agreement Management |  |  | Score
| SP 1.1 | Determine Acquisition Type Determine the type of acquisition for each product or product component to be acquired
| SP 1.2 | Select Suppliers Select suppliers based on an evaluation of their ability to meet the specified requirements and established criteria
| SP 1.3 | Establish Supplier Agreements Establish and maintain formal agreements with the supplier
| SP 2.1 | Execute the Supplier Agreement Perform activities with the supplier as specified in the supplier agreement
| SP 2.2 | Monitor Selected Supplier Processes
Select, monitor, and analyze processes used by the supplier.
| SP 2.3 | Evaluate Selected Supplier Work Products
Select and evaluate work products from the supplier of custom-made products.
| SP 2.4 | Accept the Acquired Product Ensure that the supplier agreement is satisfied before accepting the acquired product
| SP 2.5 | Transition Products Transition the acquired products from the supplier to the project
| GP 2.1 | Establish an Organizational Policy Establish and maintain an organizational policy for planning and performing supplier agreement management process
| GP 2.2 | Plan the Process Establish and maintain the plan for performing the supplier agreement management process
| GP 2.3 | Provide Resources Provide adequate resources for performing the supplier agreement management process, developing the work products, and providing the services of the process
| GP 2.4 | Assign Responsibility Assign responsibility and authority for performing the process, developing the work products, and providing the services of the supplier agreement management process
| GP 2.5 | Train People Train the people performing or supporting the supplier agreement management process as needed
| GP 2.6 | Manage Configurations Place designated work products of the supplier agreement management process under appropriate levels of configuration management
| GP 2.7 | Identify and Involve Relevant Stakeholders Identify and involve the relevant stakeholders of the supplier agreement management process as planned
| GP 2.8 | Monitor and Control the Process Monitor and control the supplier agreement management process against the plan for performing the process and take appropriate corrective action
| GP 2.9 | Objectively Evaluate Adherence Objectively evaluate adherence of the supplier agreement management process against its process description, standards, and procedures, and address noncompliance
| GP 2.10 | Review Status with Higher-Level Management Review the activities, status, and results of the supplier agreement management process with higher level management and resolve issues
| GP 3.1 | Establish a Defined Process Establish and maintain the description of a defined supplier agreement management process
| GP 3.2 | Collect Improvement Information Collect work products, measures, measurement results, and improvement information derived from planning and performing the supplier agreement management process to support the future use and improvement of the organization’s processes and process assets
|  | Measurement and Analysis |  |  | Score
| SP 1.1 | Establish Measurement Objectives Establish and maintain measurement objectives that are derived from identified information needs and objectives |  |  | 4
| SP 1.2 | Specify Measures Specify measures to address the measurement objectives |  |  | 5
| SP 1.3 | Specify Data Collection and Storage Procedures Specify how measurement data will be obtained and stored |  |  | 4
| SP 1.4 | Specify Analysis Procedures Specify how measurement data will be analyzed and reported |  |  | 4
| SP 2.1 | Collect Measurement Data Obtain specified measurement data |  |  | 5
| SP 2.2 | Analyze Measurement Data Analyze and interpret measurement data |  |  | 3
| SP 2.3 | Store Data and Results Manage and store measurement data, measurement specifications, and analysis results |  |  | 4
| SP 2.4 | Communicate Results Report results of measurement and analysis activities to all relevant stakeholders |  |  | 7
| GP 2.1 | Establish an Organizational Policy Establish and maintain an organizational policy for planning and performing the measurement and analysis process |  |  | 4
| GP 2.2 | Plan the Process Establish and maintain the plan for performing the measurement and analysis process |  |  | 4
| GP 2.3 | Provide Resources Provide adequate resources for performing the measurement and analysis process, developing the work products, and providing the services of the process |  |  | 6
| GP 2.4 | Assign Responsibility Assign responsibility and authority for performing the process, developing the work products, and providing the services of the measurement and analysis process |  |  | 8
| GP 2.5 | Train People Train the people performing or supporting the measurement and analysis process as needed |  |  | 4
| GP 2.6 | Manage Configurations Place designated work products of the measurement and analysis process under appropriate levels of configuration management |  |  | 10
| GP 2.7 | Identify and Involve Relevant Stakeholders Identify and involve the relevant stakeholders of the measurement and analysis process as planned |  |  | 6
| GP 2.8 | Monitor and Control the Process Monitor and control the measurement and analysis process against the plan for performing the process and take appropriate corrective action |  |  | 6
| GP 2.9 | Objectively Evaluate Adherence Objectively evaluate adherence of the measurement and analysis process against its process description, standards, and procedures, and address noncompliance |  |  | 4
| GP 2.10 | Review Status with Higher-Level Management Review the activities, status, and results of the measurement and analysis process with higher level management and resolve issues |  |  | 6
| GP 3.1 | Establish a Defined Process Establish and maintain the description of a defined measurement and analysis process |  |  | 4
| GP 3.2 | Collect Improvement Information Collect work products, measures, measurement results, and improvement information derived from planning and performing the measurement and analysis process to support the future use and improvement of the organization’s processes and process assets |  |  | 4
|  | Process and Product Quality Assurance |  |  | Score
| SP 1.1 | Objectively Evaluate Processes Objectively evaluate the designated performed processes against the applicable process descriptions, standards and procedures |  |  | 6
| SP 1.2 | Objectively Evaluate Work Products and Services Objectively evaluate the designated work products and services against the applicable process descriptions, standards, and procedures |  |  | 7
| SP 2.1 | Communicate and Ensure Resolution of Noncompliance Issues Communicate quality issues and ensure resolution of noncompliance issues with the staff and managers |  |  | 6
| SP 2.2 | Establish Records Establish and maintain records of the quality assurance activities |  |  | 6
| GP 2.1 | Establish an Organizational Policy Establish and maintain an organizational policy for planning and performing the process and product quality assurance process | 1
| GP 2.2 | Plan the Process Establish and maintain the plan for performing the process and product quality assurance process |  |  | 5
| GP 2.3 | Provide Resources Provide adequate resources for performing the process and product quality assurance process, developing the work products, and providing the services of the process |  |  | 4
| GP 2.4 | Assign Responsibility Assign responsibility and authority for performing the process, developing the work products, and providing the services of the process and product quality assurance process |  |  | 5
| GP 2.5 | Train People Train the people performing or supporting the process and product quality assurance process as needed |  |  | 3
| GP 2.6 | Manage Configurations Place designated work products of the process and product quality assurance process under appropriate levels of configuration management |  |  | 5
| GP 2.7 | Identify and Involve Relevant Stakeholders Identify and involve the relevant stakeholders of the process and product quality assurance process as planned | 1
| GP 2.8 | Monitor and Control the Process Monitor and control the process and product quality assurance process against the plan for performing the process and take appropriate corrective action |  |  | 5
| GP 2.9 | Objectively Evaluate Adherence Provide adequate resources for performing the process and product quality assurance process, developing the work products, and providing the services of the process |  |  | 6
| GP 2.10 | Review Status with Higher-Level Management Review the activities, status, and results of the process and product quality assurance process with higher level management and resolve issues | 1
| GP 3.1 | Establish a Defined Process Establish and maintain the description of a defined process and product quality assurance process
| GP 3.2 | Collect Improvement Information Collect work products, measures, measurement results, and improvement information derived from planning and performing the process and product quality assurance process to support the future use and improvement of the organization’s processes and process assets
|  | Configuration Management |  |  | Score
| SP 1.1 | Identify Configuration Items Identify the configuration items, components, and related work products that will be placed under configuration management |  |  | 7
| SP 1.2 | Establish a Configuration Management System Establish and maintain a configuration management and change management system for controlling work products |  |  | 7
| SP 1.3 | Create or Release Baselines Create or release baselines for internal use and for delivery to the customer |  |  | 5
| SP 2.1 | Track Changes Track change requests for the configuration items |  |  | 4
| SP 2.2 | Control Changes Control changes to the configuration items |  |  | 7
| SP 3.1 | Establish Configuration Management Records Establish and maintain records describing configuration items |  |  | 5
| SP 3.2 | Perform Configuration Audits Perform configuration audits to maintain integrity of the configuration baselines |  |  | 6
| GP 2.1 | Establish an Organizational Policy Establish and maintain an organizational policy for planning and performing the configuration management process |  |  | 4
| GP 2.2 | Plan the Process Establish and maintain the plan for performing the configuration management process |  |  | 6
| GP 2.3 | Provide Resources Provide adequate resources for performing the configuration management process, developing the work products, and providing the services of the process |  |  | 6
| GP 2.4 | Assign Responsibility Assign responsibility and authority for performing the process, developing the work products, and providing the services of the configuration management process |  |  | 7
| GP 2.5 | Train People Train the people performing or supporting the configuration management process as needed |  |  | 4
| GP 2.6 | Manage Configurations Place designated work products of the configuration management process under appropriate levels of configuration management |  |  | 8
| GP 2.7 | Identify and Involve Relevant Stakeholders Identify and involve the relevant stakeholders of the configuration management process as planned |  |  | 8
| GP 2.8 | Monitor and Control the Process Monitor and control the configuration management process against the plan for performing the process and take appropriate corrective action |  |  | 6
| GP 2.9 | Objectively Evaluate Adherence Objectively evaluate adherence of the configuration management process against its process description, standards, and procedures, and address noncompliance |  |  | 5
| GP 2.10 | Review Status with Higher-Level Management Review the activities, status, and results of the configuration management process with higher level management and resolve issues |  |  | 4
| GP 3.1 | Establish a Defined Process Establish and maintain the description of a defined configuration management process |  |  | 4
| GP 3.2 | Collect Improvement Information Collect work products, measures, measurement results, and improvement information derived from planning and performing the configuration management process to support the future use and improvement of the organization’s processes and process assets |  |  | 4
Level 3
|  | Requirements Development |  |  | Score
| SP 1.1 | Elicit Needs Elicit stakeholder needs, expectations, constraints, and interfaces for all phases of the product's life cycle
| SP 1.2 | Transform Stakeholder Needs, Expectations, Constraints, and Interfaces into Customer Requirements Transform stakeholder needs, expectations, constraints, and interfaces into customer requirements
| SP 2.1 | Establish Product and Product Component Requirements Establish and maintain product and product component requirements, which are based on the customer requirements
| SP 2.2 | Allocate Product Component Requirements Allocate the requirements for each product component
| SP 2.3 | Identify Interface Requirements Identify interface requirements
| SP 3.1 | Establish Operational Concepts and Scenarios Establish and maintain operational concepts and associated scenarios
| SP 3.2 | Establish a Definition of Required Functionality Establish and maintain a definition of required functionality
| SP 3.3 | Analyze Requirements Analyze requirements to ensure that they are necessary and sufficient
| SP 3.4 | Analyze Requirements to Achieve Balance Analyze requirements to balance stakeholder needs and constraints
| SP 3.5 | Validate Requirements with Comprehensive Methods Validate requirements to ensure the resulting product will perform as intended in the user's environment
| GP 2.1 | Establish an Organizational Policy Establish and maintain an organizational policy for planning and performing the requirements development process
| GP 2.2 | Plan the Process Establish and maintain the plan for performing the requirements development process
| GP 2.3 | Provide Resources Provide adequate resources for performing the requirements development process, developing the work products, and providing the services of the process
| GP 2.4 | Assign Responsibility Assign responsibility and authority for performing the process, developing the work products, and providing the services of the requirements development process
| GP 2.5 | Train People Train the people performing or supporting the requirements development process as needed
| GP 2.6 | Manage Configurations Place designated work products of the requirements development process under appropriate levels of configuration management
| GP 2.7 | Identify and Involve Relevant Stakeholders Identify and involve the relevant stakeholders of the requirements development process as planned
| GP 2.8 | Monitor and Control the Process Monitor and control the requirements development process against the plan for performing the process and take appropriate corrective action
| GP 2.9 | Objectively Evaluate Adherence Objectively evaluate adherence of the requirements development process against its process description, standards, and procedures, and address noncompliance
| GP 2.10 | Review Status with Higher-Level Management Review the activities, status, and results of the requirements development process with higher level management and resolve issues
| GP 3.1 | Establish a Defined Process Establish and maintain the description of a defined requirements development process
| GP 3.2 | Collect Improvement Information Collect work products, measures, and improvement information derived from planning and performing the requirements development process to support the future use and improvement of the organization's processes and process assets
|  | Technical Solution |  |  | Score
| SP 1.1 | Develop Alternative Solutions and Selection Criteria Develop alternative solutions and selection criteria
| SP 1.2 | Select Product-Component Solutions Select the product-component solutions that best satisfy the criteria established
| SP 2.1 | Design the Product or Product Component Develop a design for the product or product component
| SP 2.2 | Establish a Technical Data Package Establish and maintain a technical data package
| SP 2.3 | Design Interfaces Using Criteria Design product-component interfaces using established criteria
| SP 2.4 | Perform Make, Buy, or Reuse Analyses Evaluate whether the product components should be developed, purchased, or reused based on established criteria
| SP 3.1 | Implement the Design Implement the designs of the product components
| SP 3.2 | Establish Product Support Documentation Establish and maintain the end-use documentation
| GP 2.1 | Establish an Organizational Policy Establish and maintain an organizational policy for planning and performing the technical solution process
| GP 2.2 | Plan the Process Establish and maintain the plan for performing the technical solution process
| GP 2.3 | Provide Resources Provide adequate resources for performing the technical solution process, developing the work products, and providing the services of the process
| GP 2.4 | Assign Responsibility Assign responsibility and authority for performing the process, developing the work products, and providing the services of the technical solution process
| GP 2.5 | Train People Train the people performing or supporting the technical solution process as needed
| GP 2.6 | Manage Configurations Place designated work products of the technical solution process under appropriate levels of configuration management
| GP 2.7 | Identify and Involve Relevant Stakeholders Identify and involve the relevant stakeholders of the technical solution process as planned
| GP 2.8 | Monitor and Control the Process Monitor and control the technical solution process against the plan for performing the process and take appropriate corrective action
| GP 2.9 | Objectively Evaluate Adherence Objectively evaluate adherence of the technical solution process against its process description, standards, and procedures, and address noncompliance
| GP 2.10 | Review Status with Higher-Level Management Review the activities, status, and results of the technical solution process with higher level management and resolve issues
| GP 3.1 | Establish a Defined Process Establish and maintain the description of a defined technical solution process
| GP 3.2 | Collect Improvement Information Collect work products, measures, and improvement information derived from planning and performing the technical solution process to support the future use and improvement of the organization's processes and process assets
|  | Product Integration |  |  | Score
| SP 1.1 | Determine Integration Sequence Determine the product component integration sequence
| SP 1.2 | Establish the Product Integration Environment Establish and maintain the environment needed to support the integration of the product components
| SP 1.3 | Establish Product Integration Procedures and Criteria Establish and maintain procedures and criteria for integration of the product components
| SP 2.1 | Review Interface Descriptions for Completeness Review interface descriptions for coverage and completeness
| SP 2.2 | Manage Interfaces Manage internal and external interface definitions, designs, and changes for products and product components
| SP 3.1 | Confirm Readiness of Product Components for Integration Confirm, prior to assembly, that each product component required to assemble the product has been properly identified, functions according to its description, and that the product component interfaces comply with the interface descriptions
| SP 3.2 | Assemble Product Components Assemble product components according to the product integration sequence and available procedures
| SP 3.3 | Evaluate Assembled Product Components Evaluate assembled product components for interface compatibility
| SP 3.4 | Package and Deliver the Product or Product Component Package the assembled product or product component and deliver it to the appropriate customer
| GP 2.1 | Establish an Organizational Policy Establish and maintain an organizational policy for planning and performing the product integration process
| GP 2.2 | Plan the Process Establish and maintain the plan for performing the product integration process
| GP 2.3 | Provide Resources Provide adequate resources for performing the product integration process, developing the work products, and providing the services of the process
| GP 2.4 | Assign Responsibility Assign responsibility and authority for performing the process, developing the work products, and providing the services of the product integration A process
| GP 2.5 | Train People Train the people performing or supporting the product integration process as needed
| GP 2.6 | Manage Configurations Place designated work products of the product integration process under appropriate levels of configuration management
| GP 2.7 | Identify and Involve Relevant Stakeholders Identify and involve the relevant stakeholders of the product integration process as planned
| GP 2.8 | Monitor and Control the Process Monitor and control the product integration process against the plan for performing the process and take appropriate corrective action
| GP 2.9 | Objectively Evaluate Adherence Objectively evaluate adherence of the product integration process against its process description, standards, and procedures, and address noncompliance
| GP 2.10 | Review Status with Higher-Level Management Review the activities, status, and results of the product integration process with higher level management and resolve issues
| GP 3.1 | Establish a Defined Process Establish and maintain the description of a defined product integration process
| GP 3.2 | Collect Improvement Information Collect work products, measures, and improvement information derived from planning and performing the product integration process to support the future use and improvement of the organization's processes and process assets
|  | Verification |  |  | Score
| SP 1.1 | Select Work Products for Verification Select the work products to be verified and the verification methods that will be used for each
| SP 1.2 | Establish the Verification Environment Establish and maintain the environment needed to support verification
| SP 1.3 | Establish Verification Procedures and Criteria Establish and maintain verification procedures and criteria for the selected work products
| SP 2.1 | Prepare for Peer Reviews Prepare for peer reviews of selected work products
| SP 2.2 | Conduct Peer Reviews Conduct peer reviews on selected work products and identify issues resulting from the peer review
| SP 2.3 | Analyze Peer Review Data Analyze data about preparation, conduct, and results of the peer reviews
| SP 3.1 | Perform Verification Perform verification on the selected work products
| SP 3.2 | Analyze Verification Results Analyze the results of all verification activities
| GP 2.1 | Establish an Organizational Policy Establish and maintain an organizational policy for planning and performing the verification process
| GP 2.2 | Plan the Process Establish and maintain the plan for performing the verification process
| GP 2.3 | Provide Resources Provide adequate resources for performing the verification process, developing the work products, and providing the services of the process
| GP 2.4 | Assign Responsibility Assign responsibility and authority for performing the process, developing the work products, and providing the services of the verification process
| GP 2.5 | Train People Train the people performing or supporting the verification process as needed
| GP 2.6 | Manage Configurations Place designated work products of the verification process under appropriate levels of configuration management
| GP 2.7 | Identify and Involve Relevant Stakeholders Identify and involve the relevant stakeholders of the verification process as planned
| GP 2.8 | Monitor and Control the Process Monitor and control the verification process against the plan for performing the process and take appropriate corrective action
| GP 2.9 | Objectively Evaluate Adherence Objectively evaluate adherence of the verification process against its process description, standards, and procedures, and address noncompliance
| GP 2.10 | Review Status with Higher-Level Management Review the activities, status, and results of the verification process with higher level management and resolve issues
| GP 3.1 | Establish a Defined Process Establish and maintain the description of a defined verification process
| GP 3.2 | Collect Improvement Information Collect work products, measures, and improvement information derived from planning and performing the verification process to support the future use and improvement of the organization's processes and process assets
|  | Validation |  |  | Score
| SP 1.1 | Select Products for Validation Select products and product components to be validated and the validation methods that will be used for each
| SP 1.2 | Establish the Validation Environment Establish and maintain the environment needed to support validation
| SP 1.3 | Establish Validation Procedures and Criteria Establish and maintain procedures and criteria for validation
| SP 2.1 | Perform Validation Perform validation on the selected products and product components
| SP 2.2 | Analyze Validation Results Analyze the results of the validation activities
| GP 2.1 | Establish an Organizational Policy Establish and maintain an organizational policy for planning and performing the validation process
| GP 2.2 | Plan the Process Establish and maintain the plan for performing the validation process
| GP 2.3 | Provide Resources Provide adequate resources for performing the validation process, developing the work products, and providing the services of the process
| GP 2.4 | Assign Responsibility Assign responsibility and authority for performing the process, developing the work products, and providing the services of the validation process
| GP 2.5 | Train People Train the people performing or supporting the validation process as needed
| GP 2.6 | Manage Configurations Place designated work products of the validation process under appropriate levels of configuration management
| GP 2.7 | Identify and Involve Relevant Stakeholders Identify and involve the relevant stakeholders of the validation process as planned
| GP 2.8 | Monitor and Control the Process Monitor and control the validation process against the plan for performing the process and take appropriate corrective action
| GP 2.9 | Objectively Evaluate Adherence Objectively evaluate adherence of the validation process against its process description, standards, and procedures, and address noncompliance
| GP 2.10 | Review Status with Higher-Level Management Review the activities, status, and results of the validation process with higher level management and resolve issues
| GP 3.1 | Establish a Defined Process Establish and maintain the description of a defined validation process
| GP 3.2 | Collect Improvement Information Collect work products, measures, and improvement information derived from planning and performing the validation process to support the future use and improvement of the organization's processes and process assets
|  | Organizational Process Focus |  |  | Score
| SP 1.1 | Establish Organizational Process Needs Establish and maintain the description of the process needs and objectives for the organization
| SP 1.2 | Appraise the Organization's Processes Appraise the processes of the organization periodically and as needed to maintain an understanding of their strengths and weaknesses
| SP 1.3 | Identify the Organization's Process Improvements Identify improvements to the organization's processes and process assets
| SP 2.1 | Establish Process Action Plans Establish and maintain process action plans to address improvements to the organization's processes and process assets
| SP 2.2 | Implement Process Action Plans Implement process action plans
| SP 3.1 | Deploy Organizational Process Assets Deploy the organizational process assets across the organization
| SP 3.2 | Deploy Standard Processes
Deploy the organization’s set of standard processes to projects at their startup and deploy changes to them as appropriate throughout the life of each project.
| SP 3.3 | Monitor Implementation
Monitor the implementation of the organization’s set of standard processes and use of process assets on all projects.
| SP 3.4 | Incorporate Process-Related Experiences into the Organizational Process Assets Incorporate process-related work products, measures, and improvement information derived from planning and performing the process into the organizational process assets
| GP 2.1 | Establish an Organizational Policy Establish and maintain an organizational policy for planning and performing the organizational process focus process
| GP 2.2 | Plan the Process Establish and maintain the plan for performing the organizational process focus process
| GP 2.3 | Provide Resources Provide adequate resources for performing the organizational process focus process, developing the work products, and providing the services of the process
| GP 2.4 | Assign Responsibility Assign responsibility and authority for performing the process, developing the work products, and providing the services of the organizational process focus process
| GP 2.5 | Train People Train the people performing or supporting the organizational process focus process as needed
| GP 2.6 | Manage Configurations Place designated work products of the organizational process focus process under appropriate levels of configuration management
| GP 2.7 | Identify and Involve Relevant Stakeholders Identify and involve the relevant stakeholders of the organizational process focus process as planned
| GP 2.8 | Monitor and Control the Process Monitor and control the organizational process focus process against the plan for performing the process and take appropriate corrective action
| GP 2.9 | Objectively Evaluate Adherence Objectively evaluate adherence of the organizational process focus process against its process description, standards, and procedures, and address noncompliance
| GP 2.10 | Review Status with Higher-Level Management Review the activities, status, and results of the organizational process focus process with higher level management and resolve issues
| GP 3.1 | Establish a Defined Process Establish and maintain the description of a defined organizational process focus process
| GP 3.2 | Collect Improvement Information Collect work products, measures, and improvement information derived from planning and performing the organizational process focus process to support the future use and improvement of the organization's processes and process assets
|  | Organizational Process Definition |  |  | Score
| SP 1.1 | Establish Standard Processes Establish and maintain the organization's set of standard processes
| SP 1.2 | Establish Life-Cycle Model Descriptions Establish and maintain descriptions of the life-cycle process models approved for use in the organization
| SP 1.3 | Establish Tailoring Criteria and Guidelines Establish and maintain the tailoring criteria and guidelines for the organization's set of standard processes
| SP 1.4 | Establish the Organization’s Measurement Repository Establish and maintain the organization’s measurement repository
| SP 1.5 | Establish the Organization’s Process Asset Library Establish and maintain the organization's process asset library
| SP 1.6 | Establish Work Environment Standards
Establish and maintain work environment standards
| SP 2.1 | (IPPD only) Establish Empowerment Mechanisms
Establish and maintain empowerment mechanisms to enable timely decision making.
| SP 2.2 | (IPPD only) Establish Rules and Guidelines for Integrated Teams
Establish and maintain organizational rules and guidelines for structuring and forming integrated teams.
| SP 2.3 | (IPPD only) Balance Team and Home Organization Responsibilities
Establish and maintain organizational guidelines to help team members balance their team and home organization responsibilities.
| GP 2.1 | Establish an Organizational Policy Establish and maintain an organizational policy for planning and performing the organizational process definition process
| GP 2.2 | Plan the Process Establish and maintain the plan for performing the organizational process definition process
| GP 2.3 | Provide Resources Provide adequate resources for performing the organizational process definition process, developing the work products, and providing the services of the process
| GP 2.4 | Assign Responsibility Assign responsibility and authority for performing the process, developing the work products, and providing the services of the organizational process definition process
| GP 2.5 | Train People Train the people performing or supporting the organizational process definition process as needed
| GP 2.6 | Manage Configurations Place designated work products of the organizational process definition process under appropriate levels of configuration management
| GP 2.7 | Identify and Involve Relevant Stakeholders Identify and involve the relevant stakeholders of the organizational process definition process as planned
| GP 2.8 | Monitor and Control the Process Monitor and control the organizational process definition process against the plan for performing the process and take appropriate corrective action
| GP 2.9 | Objectively Evaluate Adherence Objectively evaluate adherence of the organizational process definition process against its process description, standards, and procedures, and address noncompliance
| GP 2.10 | Review Status with Higher-Level Management Review the activities, status, and results of the organizational process definition process with higher level management and resolve issues
| GP 3.1 | Establish a Defined Process Establish and maintain the description of a defined organizational process definition process
| GP 3.2 | Collect Improvement Information Collect work products, measures, and improvement information derived from planning and performing the organizational process definition process to support the future use and improvement of the organization's processes and process assets
|  | Organizational Training |  |  | Score
| SP 1.1 | Establish the Strategic Training needs Establish and maintain the strategic training needs of the organization
| SP 1.2 | Determine Which Training Needs Are the Responsibility of the Organization Determine which training needs are the responsibility of the organization and which will be left to the individual project or support group
| SP 1.3 | Establish an Organizational Training Tactical Plan Establish and maintain an organizational training tactical plan
| SP 1.4 | Establish Training Capability Establish and maintain training capability to address organizational training needs
| SP 2.1 | Deliver Training Deliver the training following an organizational training plan
| SP 2.2 | Establish Training Records Establish and maintain records of the organizational training
| SP 2.3 | Assess Training Effectiveness Assess the effectiveness of the organization's training program
| GP 2.1 | Establish an Organizational Policy Establish and maintain an organizational policy for planning and performing the organizational training process
| GP 2.2 | Plan the Process Establish and maintain the plan for performing the organizational training process
| GP 2.3 | Provide Resources Provide adequate resources for performing the organizational training process, developing the work products, and providing the services of the process
| GP 2.4 | Assign Responsibility Assign responsibility and authority for performing the process, developing the work products, and providing the services of the organizational training process
| GP 2.5 | Train People Train the people performing or supporting the organizational training process as needed
| GP 2.6 | Manage Configurations Place designated work products of the organizational training process under appropriate levels of configuration management
| GP 2.7 | Identify and Involve Relevant Stakeholders Identify and involve the relevant stakeholders of the organizational training process as planned
| GP 2.8 | Monitor and Control the Process Monitor and control the organizational training process against the plan for performing the process and take appropriate corrective action
| GP 2.9 | Objectively Evaluate Adherence Objectively evaluate adherence of the organizational training process against its process description, standards, and procedures, and address noncompliance
| GP 2.10 | Review Status with Higher-Level Management Review the activities, status, and results of the organizational training process with higher level management and resolve issues
| GP 3.1 | Establish a Defined Process Establish and maintain the description of a defined organizational training process
| GP 3.2 | Collect Improvement Information Collect work products, measures, and improvement information derived from planning and performing the organizational training process to support the future use and improvement of the organization's processes and process assets
|  | Integrated Project Management |  |  | Score
| SP 1.1 | Establish the Project's Defined Process Establish and maintain the project's defined process from project startup through the life of the project
| SP 1.2 | Use Organizational Process Assets for Planning Project Activities Use the organization's process assets and measurement repository for estimating and planning the project's activities
| SP 1.3 | Establish the Project's Work Environment
Establish and maintain the project's work environment based on the organization's work environment standards
| SP 1.4 | Integrate Plans Integrate the project plan and the other plans that affect the project to describe the project’s defined process
| SP 1.5 | Manage the Project Using the Integrated Plans Manage the project using the project plan, the other plans that affect the project, and the project’s defined process
| SP 1.6 | Contribute to the Organization's Process Assets Contribute work products, measures, and documented experiences to the organizational process assets
| SP 2.1 | Manage Stakeholder Involvement Manage the involvement of the relevant stakeholders in the project
| SP 2.2 | Manage Dependencies Participate with relevant stakeholders to identify, negotiate, and track critical dependencies
| SP 2.3 | Resolve Coordination Issues Resolve issues with relevant stakeholders
| SP 3.1 | (IPPD only) Establish the Project’s Shared Vision
Establish and maintain a shared vision for the project
| SP 3.2 | (IPPD only) Establish the Integrated Team Structure
Establish and maintain the integrated team structure for the project.
| SP 3.3 | (IPPD only) Allocate Requirements to Integrated Teams
Allocate requirements, responsibilities, tasks, and interfaces to teams in the integrated team structure
| SP 3.4 | (IPPD only) Establish Integrated Teams
Establish and maintain integrated teams in the structure
| SP 3.5 | (IPPD only) Ensure Collaboration among Interfacing Teams
Ensure collaboration among interfacing teams
| GP 2.1 | Establish an Organizational Policy Establish and maintain an organizational policy for planning and performing the integrated project management process
| GP 2.2 | Plan the Process Establish and maintain the plan for performing the integrated project management process
| GP 2.3 | Provide Resources Provide adequate resources for performing the integrated project management process, developing the work products, and providing the services of the process
| GP 2.4 | Assign Responsibility Assign responsibility and authority for performing the process, developing the work products, and providing the services of the integrated project management process
| GP 2.5 | Train People Train the people performing or supporting the integrated project management process as needed
| GP 2.6 | Manage Configurations Place designated work products of the integrated project management process under appropriate levels of configuration management
| GP 2.7 | Identify and Involve Relevant Stakeholders Identify and involve the relevant stakeholders of the integrated project management process as planned
| GP 2.8 | Monitor and Control the Process Monitor and control the integrated project management process against the plan for performing the process and take appropriate corrective action
| GP 2.9 | Objectively Evaluate Adherence Objectively evaluate adherence of the integrated project management process against its process description, standards, and procedures, and address noncompliance
| GP 2.10 | Review Status with Higher-Level Management Review the activities, status, and results of the integrated project management process with higher level management and resolve issues
| GP 3.1 | Establish a Defined Process Establish and maintain the description of a defined integrated project management process
| GP 3.2 | Collect Improvement Information Collect work products, measures, and improvement information derived from planning and performing the integrated project management process to support the future use and improvement of the organization's processes and process assets
|  | Risk Management |  |  | Score
| SP 1.1 | Determine Risk Sources and Categories Determine risk sources and categories
| SP 1.2 | Define Risk Parameters Define the parameters used to analyze and categorize risks, and the parameters used to control the risk management effort
| SP 1.3 | Establish a Risk Management Strategy Establish and maintain the strategy and methods to be used for risk management
| SP 2.1 | Identify Risks Identify and document the risks
| SP 2.2 | Evaluate, Categorize, and Prioritize Risks Evaluate and categorize each identified risk using the defined risk categories and parameters, and determine its relative priority
| SP 3.1 | Develop Risk Mitigation Plans Develop a risk mitigation plan for the most important risks to the project, as defined by the risk management strategy
| SP 3.2 | Implement Risk Mitigation Plans Monitor the status of each risk periodically and implement the risk mitigation plan as appropriate
| GP 2.1 | Establish an Organizational Policy Establish and maintain an organizational policy for planning and performing the risk management process
| GP 2.2 | Plan the Process Establish and maintain the plan for performing the risk management process
| GP 2.3 | Provide Resources Provide adequate resources for performing the risk management process, developing the work products, and providing the services of the process
| GP 2.4 | Assign Responsibility Assign responsibility and authority for performing the process, developing the work products, and providing the services of the risk management process
| GP 2.5 | Train People Train the people performing or supporting the risk management process as needed
| GP 2.6 | Manage Configurations Place designated work products of the risk management process under appropriate levels of configuration management
| GP 2.7 | Identify and Involve Relevant Stakeholders Identify and involve the relevant stakeholders of the risk management process as planned
| GP 2.8 | Monitor and Control the Process Monitor and control the risk management process against the plan for performing the process and take appropriate corrective action
| GP 2.9 | Objectively Evaluate Adherence Objectively evaluate adherence of the risk management process against its process description, standards, and procedures, and address noncompliance
| GP 2.10 | Review Status with Higher-Level Management Review the activities, status, and results of the risk management process with higher level management and resolve issues
| GP 3.1 | Establish a Defined Process Establish and maintain the description of a defined risk management process
| GP 3.2 | Collect Improvement Information Collect work products, measures, and improvement information derived from planning and performing the risk management process to support the future use and improvement of the organization's processes and process assets
|  | Decision Analysis and Resolution |  |  | Score
| SP 1.1 | Establish Guidelines for Decision Analysis Establish and maintain guidelines to determine which issues are subject to a formal evaluation process
| SP 1.2 | Establish Evaluation Criteria Establish and maintain the criteria for evaluating alternatives, and the relative ranking of these criteria
| SP 1.3 | Identify Alternative Solutions Identify alternative solutions to address issues
| SP 1.4 | Select Evaluation Methods Select the evaluation methods
| SP 1.5 | Evaluate Alternatives Evaluate alternative solutions using the established criteria and methods
| SP 1.6 | Select Solutions Select solutions from the alternatives based on the evaluation criteria
| GP 2.1 | Establish an Organizational Policy Establish and maintain an organizational policy for planning and performing the decision analysis and resolution process
| GP 2.2 | Plan the Process Establish and maintain the plan for performing the decision analysis and resolution process
| GP 2.3 | Provide Resources Provide adequate resources for performing the planned process, developing the work products and providing the services for the decision analysis and resolution process
| GP 2.4 | Assign Responsibility Assign responsibility and authority for performing the process, developing the work products, and providing the services of the decision analysis and resolution process
| GP 2.5 | Train People Train the people performing or supporting the decision analysis and resolution process as needed
| GP 2.6 | Manage Configurations Place designated work products of the decision analysis and resolution process under appropriate levels of configuration management
| GP 2.7 | Identify and Involve Relevant Stakeholders Identify and involve the relevant stakeholders of the decision analysis and resolution process as planned
| GP 2.8 | Monitor and Control the Process Monitor and control the decision analysis and resolution process against the plan and take appropriate corrective action
| GP 2.9 | Objectively Evaluate Adherence Objectively evaluate adherence of the decision analysis and resolution process and the work products and services of the process to the applicable requirements, objectives, and standards, and address noncompliance
| GP 2.10 | Review Status with Higher-Level Management Review the activities, status, and results of the decision analysis and resolution process with management and resolve issues
| GP 3.1 | Establish a Defined Process Establish and maintain the description of a defined decision analysis and resolution process
| GP 3.2 | Collect Improvement Information Collect work products, measures, and improvement information derived from planning and performing the decision analysis and resolution process to support the future use and improvement of the organization's processes and process assets
Level 4
|  | Organizational Process Performance |  |  | Score
| SP 1.1 | Select Processes Select the processes or process elements in the organization's set of standard processes that are to be included in the organization's process performance analyses
| SP 1.2 | Establish Process Performance Measures Establish and maintain definitions of the measures that are to be included in the organization's process performance analyses
| SP 1.3 | Establish Quality and Process Performance Objectives Establish and maintain quantitative objectives for quality and process performance for the organization
| SP 1.4 | Establish Process Performance Baselines Establish and maintain the organization's process performance baselines
| SP 1.5 | Establish Process Performance Models Establish and maintain the process performance models for the organization's set of standard processes
| GP 2.1 | Establish an Organizational Policy Establish and maintain an organizational policy for planning and performing the organizational process performance process
| GP 2.2 | Plan the Process Establish and maintain the plan for performing the organizational process performance process
| GP 2.3 | Provide Resources Provide adequate resources for performing the organizational process performance process, developing the work products, and providing the services of the process
| GP 2.4 | Assign Responsibility Assign responsibility and authority for performing the process, developing the work products, and providing the services of the organizational process performance process
| GP 2.5 | Train People Train the people performing or supporting the organizational process performance process as needed
| GP 2.6 | Manage Configurations Place designated work products of the organizational process performance process under appropriate levels of configuration management
| GP 2.7 | Identify and Involve Relevant Stakeholders Identify and involve the relevant stakeholders of the organizational process performance process as planned
| GP 2.8 | Monitor and Control the Process Monitor and control the organizational process performance process against the plan for performing the process and take appropriate corrective action
| GP 2.9 | Objectively Evaluate Adherence Objectively evaluate adherence of the organizational process performance process against its process description, standards, and procedures, and address noncompliance
| GP 2.10 | Review Status with Higher-Level Management Review the activities, status, and results of the organizational process performance process with higher level management and resolve issues
| GP 3.1 | Establish a Defined Process Establish and maintain the description of a defined organizational process performance process
| GP 3.2 | Collect Improvement Information Collect work products, measures, and improvement information derived from planning and performing the organizational process performance process to support the future use and improvement of the organization's processes and process assets
|  | Quantitative Project Management |  |  | Score
| SP 1.1 | Establish the Project's Objectives Establish and maintain the project's quality and process performance objectives
| SP 1.2 | Compose the Defined Process Select the sub-processes that compose the project’s defined process based on historical stability and capability data
| SP 1.3 | Select the Sub-processes that Will Be Statistically Managed Select the sub-processes of the project's defined process that will be statistically managed
| SP 1.4 | Manage Project Performance Monitor the project to determine whether the project's objectives for quality and process performance will be satisfied, and identify corrective action as appropriate
| SP 2.1 | Select Measures and Analytic Techniques Select the measures and analytic techniques to be used in statistically managing the selected sub-processes
| SP 2.2 | Apply Statistical Methods to Understand Variation Establish and maintain an understanding of the variation of the selected sub-processes using the selected measures and analytic techniques
| SP 2.3 | Monitor Performance of the Selected Sub-processes Monitor the performance of the selected sub-processes to determine their capability to satisfy their quality and process performance objectives, and identify corrective action as necessary
| SP 2.4 | Record Statistical Management Data Record statistical and quality management data in the organization's measurement repository
| GP 2.1 | Establish an Organizational Policy Establish and maintain an organizational policy for planning and performing the quantitative project management process
| GP 2.2 | Plan the Process Establish and maintain the plan for performing the quantitative project management process
| GP 2.3 | Provide Resources Provide adequate resources for performing the quantitative project management process, developing the work products, and providing the services of the process
| GP 2.4 | Assign Responsibility Assign responsibility and authority for performing the process, developing the work products, and providing the services of the quantitative project management process
| GP 2.5 | Train People Train the people performing or supporting the quantitative project management process as needed
| GP 2.6 | Manage Configurations Place designated work products of the quantitative project management process under appropriate levels of configuration management
| GP 2.7 | Identify and Involve Relevant Stakeholders Identify and involve the relevant stakeholders of the quantitative project management process as planned
| GP 2.8 | Monitor and Control the Process Monitor and control the quantitative project management process against the plan for performing the process and take appropriate corrective action
| GP 2.9 | Objectively Evaluate Adherence Objectively evaluate adherence of the quantitative project management process against its process description, standards, and procedures, and address noncompliance
| GP 2.10 | Review Status with Higher-Level Management Review the activities, status, and results of the quantitative project management process with higher level management and resolve issues
| GP 3.1 | Establish a Defined Process Establish and maintain the description of a defined quantitative project management process
| GP 3.2 | Collect Improvement Information Collect work products, measures, and improvement information derived from planning and performing the quantitative project management process to support the future use and improvement of the organization's processes and process assets
Level 5
|  | Organizational Innovation and Deployment |  |  | Score
| SP 1.1 | Collect and Analyze Improvement Proposals Collect and analyze process and technology improvement proposals
| SP 1.2 | Identify and Analyze Innovations Identify and analyze innovative improvements that could increase the organization’s quality and process performance
| SP 1.3 | Pilot Improvements Pilot process and technology improvements to select which ones to implement
| SP 1.4 | Select Improvements for Deployment Select process and technology improvement proposals for deployment across the organization
| SP 2.1 | Plan the Deployment Establish and maintain the plans for deploying the selected process and technology improvements
| SP 2.2 | Manage the Deployment Manage the deployment of the selected process and technology improvements
| SP 2.3 | Measure Improvement Effects Measure the effects of the deployed process and technology improvements
| GP 2.1 | Establish an Organizational Policy Establish and maintain an organizational policy for planning and performing the organizational innovation and deployment process
| GP 2.2 | Plan the Process Establish and maintain the plan for performing the organizational innovation and deployment process
| GP 2.3 | Provide Resources Provide adequate resources for performing the organizational innovation and deployment process, developing the work products, and providing the services of the process
| GP 2.4 | Assign Responsibility Assign responsibility and authority for performing the process, developing the work products, and providing the services of the organizational innovation and deployment process
| GP 2.5 | Train People Train the people performing or supporting the organizational innovation and deployment process as needed
| GP 2.6 | Manage Configurations Place designated work products of the organizational innovation and deployment process under appropriate levels of configuration management
| GP 2.7 | Identify and Involve Relevant Stakeholders Identify and involve the relevant stakeholders of the organizational innovation and deployment process as planned
| GP 2.8 | Monitor and Control the Process Monitor and control the organizational innovation and deployment process against the plan for performing the process and take appropriate corrective action
| GP 2.9 | Objectively Evaluate Adherence Objectively evaluate adherence of the organizational innovation and deployment process against its process description, standards, and procedures, and address noncompliance
| GP 2.10 | Review Status with Higher-Level Management Review the activities, status, and results of the organizational innovation and deployment process with higher level management and resolve issues
| GP 3.1 | Establish a Defined Process Establish and maintain the description of a defined organizational innovation and deployment process
| GP 3.2 | Collect Improvement Information Collect work products, measures, and improvement information derived from planning and performing the organizational innovation and deployment process to support the future use and improvement of the organization's processes and process assets
|  | Causal Analysis and Resolution |  |  | Score
| SP 1.1 | Select Defect Data for Analysis Select the defects and other problems for analysis
| SP 1.2 | Analyze Causes Perform causal analysis of selected defects and other problems and propose actions to address them
| SP 2.1 | Implement the Action Proposals Implement the selected action proposals that were developed in causal analysis
| SP 2.2 | Evaluate the Effect of Changes Evaluate the effect of changes on process performance
| SP 2.3 | Record Data Record causal analysis and resolution data for use across the project and organization
| GP 2.1 | Establish an Organizational Policy Establish and maintain an organizational policy for planning and performing the causal analysis and resolution process
| GP 2.2 | Plan the Process Establish and maintain the plan for performing the causal analysis and resolution process
| GP 2.3 | Provide Resources Provide adequate resources for performing the causal analysis and resolution process, developing the work products, and providing the services of the process
| GP 2.4 | Assign Responsibility Assign responsibility and authority for performing the process, developing the work products, and providing the services of the causal analysis and resolution process
| GP 2.5 | Train People Train the people performing or supporting the causal analysis and resolution process as needed
| GP 2.6 | Manage Configurations Place designated work products of the causal analysis and resolution process under appropriate levels of configuration management
| GP 2.7 | Identify and Involve Relevant Stakeholders Identify and involve the relevant stakeholders of the causal analysis and resolution process as planned
| GP 2.8 | Monitor and Control the Process Monitor and control the causal analysis and resolution process against the plan for performing the process and take appropriate corrective action
| GP 2.9 | Objectively Evaluate Adherence Objectively evaluate adherence of the causal analysis and resolution process against its process description, standards, and procedures, and address noncompliance
| GP 2.10 | Review Status with Higher-Level Management Review the activities, status, and results of the causal analysis and resolution process with higher level management and resolve issues
| GP 3.1 | Establish a Defined Process Establish and maintain the description of a defined causal analysis and resolution process
| GP 3.2 | Collect Improvement Information Collect work products, measures, and improvement information derived from planning and performing the causal analysis and resolution process to support the future use and improvement of the organization's processes and process assets

## Data (hidden)
Name of moderator | Erik
Date | 2011-11-27
Number of participants | 1
REQM
PP
PMC
SAM
MA
PPQA
CM
RD
TS
PI
VER
VAL
OPF
OPD
OT
IPM
RSKM
DAR
OPP
QPM
OID
CAR
1